{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Диаграмма1","Использование задач"],"not_rendered":{"charts":2,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":1},"unopened":[{"sheet":"Диаграмма1","index":0,"reason":"not_a_worksheet"}],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Использование задач","index":1,"n_rows":16,"n_cols":4,"rows_kept":16,"cut":false,"hidden":false,"merged":[]}
["Задачи","Все"]
[]
[null,null,"Data"]
["Год","Месяц","Затраты","Совокупные затраты"]
["2012","Февраль",48958.810000000005,48958.8125]
[null,"Март",111085.37,160044.17940715156]
[null,"Апрель",176633.41,336677.58597851777]
[null,"Май",193670.99,530348.56343936163]
[null,"Июнь",165708.32999999999,696056.90053419338]
[null,"Июль",265107.37,961164.26596996386]
[null,"Август",275670.99,1236835.2538076579]
[null,"Сентябрь",235412.99,1472248.2474030224]
[null,"Октябрь",174934.55000000002,1647182.7900376914]
[null,"Ноябрь",93213.21,1740396]
["2012 Итог",null,1740396.0200000003,1740396]
["Общий итог",null,1740396.0200000003,1740396]